## groupe
ETU003350 | RANDRIANOMENA Harimalala Ericka

## liste des taches
Ligne | Catégorie | Module | Page | Description tâche | Type | Qui | Estimation | Temps passé | Reste à faire | Avancement
1 | Backoffice | Gestion Reset | deleteView | Bouton de reinitialisaton | Affichage | ETU003350 | 5 | 5 | 0 | 100%
2 | Backoffice | Gestion Reset | deleteService | deleteAll | Metier | ETU003350 | 20 | 20 | 0 | 100%
3 | Backoffice | Gestion Reset | deleteView | Bouton de reinitialisaton | Integration | ETU003350 | 10 | 10 | 0 | 100%
4 | Backoffice | Gestion Import | importView | Formulaire de fichier csv | Affichage | ETU003350 | 15 | 15 | 0 | 100%
5 | Backoffice | Gestion Import | importService | importAssets | Metier | ETU003350 | 50 | 75 | -25 | 150%
6 | Backoffice | Gestion Import | importService | importAssets | Metier | ETU003350 | 50 | 0 | 50 | 0%
7 | Backoffice | Gestion Import | importService | importAssets | Metier | ETU003350 | 50 | 0 | 50 | 0%
8 | Backoffice | Gestion Import | importService | importImage | Metier | ETU003350 | 50 | 0 | 50 | 0%
9 | Backoffice | Gestion Import | importView | Integration | Integration | ETU003350 | 15 | 0 | 15 | 0%
10 | Backoffice | Gestion Protection | entreView | formulaire de code unique | Affichage | ETU003350 | 5 | 5 | 0 | 100%
11 | Backoffice | Gestion Protection | entreService | validerCode | Integration | ETU003350 | 20 | 20 | 0 | 100%
12 | Backoffice | Gestion Protection | entreView | Integration | Integration | ETU003350 | 5 | 9 | -4 | 180%
13 | Backoffice | Gestion Dashboard | dashboardView | nombre general d element et ticket | Affichage | ETU003350 | 10 | 0 | 10 | 0%
14 | Backoffice | Gestion Dashboard | dashboardService | countElement | Metier | ETU003350 | 10 | 0 | 10 | 0%
15 | Backoffice | Gestion Dashboard | dashboardService | countTicket | Metier | ETU003350 | 10 | 0 | 10 | 0%
16 | Backoffice | Gestion Dashboard | dashboardView | Integration | Integration | ETU003350 | 10 | 0 | 10 | 0%
17 | Backoffice | Gestion Ticket | ticketListView | liste des tickets | Affichage | ETU003350 | 10 | 0 | 10 | 0%
18 | Backoffice | Gestion Ticket | ticketService | getAllTicket | Metier | ETU003350 | 10 | 0 | 10 | 0%
19 | Backoffice | Gestion Ticket | ticketListView | Integration | Integration | ETU003350 | 5 | 0 | 5 | 0%
20 | Backoffice | Gestion Ticket | ticketFicheView | fiche d un ticket | Affichage | ETU003350 | 10 | 0 | 10 | 0%
21 | Backoffice | Gestion Ticket | ticketService | getById | Metier | ETU003350 | 10 | 0 | 10 | 0%
22 | Backoffice | Gestion Ticket | ticketFicheView | Integration | Integration | ETU003350 | 5 | 0 | 5 | 0%
23 | Frontoffice | Gestion Assets | assetsListView | liste des elements | Affichage | ETU003350 | 15 | 0 | 15 | 0%
24 | Frontoffice | Gestion Assets | assetsService | getItems | Metier | ETU003350 | 20 | 0 | 20 | 0%
25 | Frontoffice | Gestion Assets | assetsListView | Integration | Integration | ETU003350 | 10 | 0 | 10 | 0%
26 | Frontoffice | Gestion Assets | assetsListView | recherche multi critere | Affichage | ETU003350 | 5 | 0 | 5 | 0%
27 | Frontoffice | Gestion Assets | assetsService | searchAssets | Metier | ETU003350 | 25 | 0 | 25 | 0%
28 | Frontoffice | Gestion Assets | assetsListView | Integration | Integration | ETU003350 | 5 | 0 | 5 | 0%
29 | Frontoffice | Gestion Ticket | ticketformView | formulaire de creation de ticket | Affichage | ETU003350 | 20 | 0 | 20 | 0%
30 | Frontoffice | Gestion Ticket | ticketService | insertTicket | Metier | ETU003350 | 20 | 0 | 20 | 0%
31 | Frontoffice | Gestion Ticket | ticketformView | Integration | Integration | ETU003350 | 15 | 0 | 15 | 0%
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77

## Recap
Qui | SUM of Estimation | SUM of Temps passé | SUM of Reste à faire
ETU003350 | 520 | 159 | 361
(vide)
Total général | 520 | 159 | 361
Avancement | 30.58%

## avancement
estimation total | temps passé total | reste à faire total | avancement | dépassement
520 | 159 | 361 | 30.58% | 0%
8.6667 |  | 6.0167 | heure

## detail_avancement
Ligne | Total | 2026-05-05 | 2026-05-06 | 2026-05-07
1 | 5 | 5
2 | 20 | 20
3 | 10 | 10
4 | 15 | 15
5 | 75 | 75
6 | 0
7 | 0
8 | 0
9 | 0
10 | 5 | 5
11 | 20 | 20
12 | 9 | 9
13 | 0
14 | 0
15 | 0
16 | 0
17 | 0
18 | 0
19 | 0
20 | 0
21 | 0
22 | 0
23 | 0
24 | 0
25 | 0